## Summary
Metric | Value
Export generated (UTC) | 2026-04-19 11:21:48
Total risks | 4
Critical risks | 1
High risks | 1
Average residual score | 11.25

## Risk Register
Identifier | Title | Category | Asset | Scenario | Owner | Status | Impact | Likelihood | Control Effectiveness | Inherent Score | Residual Score | Risk Level | Existing Controls | Notes
986bb9b2-07c5-4f0c-99c3-cbfd4e657ac3 | Privilege escalation through weak admin hygiene | Ransomware | Identity and administration tier | A threat actor reuses exposed credentials and reaches an overprivileged admin account. | Security Team | Open | 5 | 4 | 20 | 20 | 16 | Critical | MFA enabled for some admins, quarterly access reviews | High-value risk because admin compromise increases blast radius across the environment.
410ee433-5cb8-4309-9411-0667b5cf0f2a | Endpoint encryption by commodity ransomware | Ransomware | Faculty laptop fleet | Phishing leads to execution of ransomware on staff endpoints during term time. | Desktop Engineering | Mitigating | 4 | 4 | 35 | 16 | 10 | Medium | Defender, mail filtering, endpoint isolation runbook | Residual score remains high because the teaching calendar limits downtime tolerance.
9c4c63eb-9a34-401e-8764-00857c13c328 | Backups unavailable during recovery | Operational | Critical backup platform | Backups are present but restoration tests are incomplete and recovery sequencing is unclear. | Infrastructure Team | Open | 5 | 3 | 10 | 15 | 14 | High | Daily backup jobs, immutable copy for selected workloads | The main weakness is confidence in restoration and recovery time.
c977f275-f3b1-49a5-9397-cb64c6449545 | Sensitive student data exposed during incident handling | Data Protection | Student records data set | Emergency file-sharing during a ransomware event bypasses normal data handling controls. | Data Protection Officer | Accepted | 4 | 2 | 40 | 8 | 5 | Low | Sensitivity labels, retention guidance, limited emergency contacts | Accepted temporarily until the incident collaboration process is rewritten.